## Sheet1
GANTT CHART (Group 41)
Personalized Hotel Recommender using Sentiment Analysis
| Activity | Start Date | End Date | Assigned to | Duration (in days) | 26th Sep 2022 | 3rd Oct 2022 | 7th Oct 2022 | 17th Oct 2022 | 24th Oct 2022 | 29th Oct 2022 | 31st Oct 2022 | 4th Nov 2022 | 5th Nov 2022 | 9th Nov 2022 | 14th Nov 2022 | 20th Nov 2022 | 21st Nov 2022 | 27th Nov 2022 | 30th Nov 2022 | 3rd Dec 2022 | 4th Dec 2022 | 5th Dec 2022
Proposal | Idea Generation | 26th Sep 2022 | 3rd Oct 2022 | Everyone | 7
| Dataset Search | 26th Sep 2022 | 3rd Oct 2022 | Everyone | 7
| Literature Review | 26th Sep 2022 | 3rd Oct 2022 | Sunil | 7
| Proposal Writeup | 3rd Oct 2022 | 7th Oct 2022 | Prasanth and Sahaj | 4
| Presentation | 3rd Oct 2022 | 7th Oct 2022 | Nigam katta and Hemanth surya | 4
| Video Recording | 3rd Oct 2022 | 7th Oct 2022 | Everyone | 4
| Gantt Chart | 3rd Oct 2022 | 7th Oct 2022 | Sunil | 4
| Github | 3rd Oct 2022 | 7th Oct 2022 | Hemanth Surya and Sunil | 4
Midterm | Data Cleaning | 7th Oct 2022 | 17th Oct 2022 | Sunil and Prasanth | 10
| Feature Selection | 17th Oct 2022 | 24th Oct 2022 | Nigam katta and Hemanth surya | 7
| Data Visualization | 17th Oct 2022 | 24th Oct 2022 | Sahaj | 7
| Model1 (Unsupervised) Implentation | 24th Oct 2022 | 29th Oct 2022 | Nigam katta , Hemanth surya and sahaj | 5
| Results Evaluation and Discussion | 29th Oct 2022 | 31st Oct 2022 | Everyone | 2
| Model2 (Supervised) Implementation | 31st Oct 2022 | 4th Nov 2022 | Sunil and Prasanth | 5
| Results Evaluation and Discussion | 4th Nov 2022 | 5th Nov 2022 | Everyone | 1
| Midterm Report Writeup | 5th Nov 2022 | 9th Nov 2022 | Everyone | 4
Final Report | Alternate Models Selection | 9th Nov 2022 | 14th Nov 2022 | Everyone | 5
| Model3 (Unsupervised) Implementation | 14th Nov 2022 | 20th Nov 2022 | Nigam katta , Hemanth surya and sahaj | 6
| Results Evaluation and Comparision | 20th Nov 2022 | 21st Nov 2022 | Everyone | 1
| Model4(Supervised) Implementation | 21st Nov 2022 | 27th Nov 2022 | Sunil and Prasanth | 6
| Results Evaluation and Comparision | 27th Nov 2022 | 30th Nov 2022 | Everyone | 3
| Visualization of Results | 30th Nov 2022 | 3rd Dec 2022 | Nigam katta and Sahaj | 3
| Final project report writeup | 27th Nov 2022 | 5th Dec 2022 | Prasanth and Sahaj | 8
| Presentation | 3rd Dec 2022 | 4th Dec 2022 | Hemanth Surya,Nigam katta and Sunil | 1
| Final Github page | 2nd Dec 2022 | 5th Dec 2022 | Hemanth Surya | 3
| Video Recording | 3rd Dec 2022 | 5th Dec 2022 | Everyone | 2